## Project Planner
Parth - Project Implementation Tracker
Shakti Ecosystem ¦ Owner: Parth Soni ¦ 1 period = 1 week, Week 1 = Mon 3 Aug 2026. Updated 06 Aug 2026. Set 'Period Highlight' to the current week. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
SATL - Email IDs for TechLabs + group | 1 | 1 | 1 | 1 | 70%
SATL - Pitch deck + brand material | 1 | 1 | 1 | 2 | 85%
SATL - Brand guidelines document | 1 | 1 | 1 | 1 | 100%
SATL - Palette decision: Nordic Blue vs gold/sage | 1 | 1 | 1 | 1 | 0%
SATL - Brand kit rollout (templates) | 2 | 2 | 0 | 0 | 0%
S1 - Website IA + design system | 1 | 2 | 1 | 2 | 50%
S1 - SoftSys hosting, cPanel email + deploy | 1 | 1 | 1 | 1 | 100%
S1 - Namecheap nameserver switch to SoftSys | 1 | 1 | 1 | 1 | 0%
S1 - DNS propagation, SSL + Force HTTPS | 1 | 2 | 0 | 0 | 0%
S1 - Live-site fixes: meta, OG, (c) 2026, form | 1 | 2 | 0 | 0 | 0%
S1 - Venture pages build | 3 | 2 | 0 | 0 | 0%
S1 - Content + contact form / CRM wiring | 5 | 1 | 0 | 0 | 0%
S1 - Analytics + SEO baseline | 2 | 2 | 0 | 0 | 0%
FC - Pitch deck + company details | 4 | 2 | 0 | 0 | 0%
FC - Website design | 6 | 2 | 0 | 0 | 0%
FC - Website build + launch | 8 | 2 | 0 | 0 | 0%
FC - SEO implementation | 10 | 3 | 0 | 0 | 0%
SG - Website design | 9 | 2 | 0 | 0 | 0%
SG - Website build + launch | 11 | 2 | 0 | 0 | 0%
GRP - Group SEO + analytics baseline | 12 | 2 | 0 | 0 | 0%
SS - 3D asset prep + reference | 5 | 2 | 0 | 0 | 0%
SS - 3D walkthrough model build | 7 | 3 | 0 | 0 | 0%
SS - Render, review + delivery | 10 | 2 | 0 | 0 | 0%
AK - DWG/BOM demo review w/ Harshit | 2 | 1 | 2 | 1 | 30%
AK - Business model document | 3 | 2 | 0 | 0 | 0%
AK - Product + GUI packaging | 5 | 3 | 0 | 0 | 0%
OR - Product Vision document | 1 | 1 | 1 | 1 | 100%
OR - Mentza integration strategy doc | 1 | 1 | 1 | 1 | 100%
OR - Platform workflow diagram | 1 | 1 | 1 | 1 | 100%
OR - Moodle/Mentza integration plan + deck content | 1 | 1 | 1 | 1 | 100%
OR - Build integration pitch deck (PPT) | 1 | 2 | 0 | 0 | 0%
OR - Mentza scoping call (API + commercials) | 1 | 2 | 0 | 0 | 0%
OR - Brand guidelines document | 1 | 1 | 1 | 1 | 100%
OR - Logo palette decision: green vs charcoal/amber | 1 | 1 | 1 | 1 | 0%
OR - V1 UI/UX design (9 modules) | 3 | 5 | 0 | 0 | 0%
OR - Branding + expansion pitch deck | 7 | 2 | 0 | 0 | 0%

## Task Register
Task Register - all tasks assigned to Parth
Source: 'Tasks Sheet.xlsx' (all 10 company tabs), rows where Who contains 'Parth', plus the 6 Aug 2026 end-of-day update. Week 1 = 03 Aug 2026. Rows marked 'NOT IN TASKS SHEET' are delivered or proposed work with no tracked row - add them upstream.
ID | Company | Task (as written in Tasks Sheet) | Owner | Support | Status | Prio | Target | Planned weeks | Deliverable | Notes / dependencies / risks | Change | Gantt row
1 | ShaktiAITechLabs | to create email address for Techlabs and check for other companies | Parth | Ekata | At risk | P0 | 7 Aug 2026 | W1-W1 (03 Aug - 09 Aug) | Working TechLabs mailboxes + alias list for other group companies | DUE TOMORROW. The cPanel/SoftSys route is now proven (shakti.one domain email created 6 Aug) - remaining work is repeating it on the TechLabs domain and agreeing the alias list with Ekata. | UPD 6 Aug | Row 5
2 | ShaktiAITechLabs | to make pitch deck and brand material for TechLabs | Parth | - | In progress | P0 | 9 Aug 2026 | W1-W1 (03 Aug - 09 Aug) | Investor/partner pitch deck + brand identity system | Brand side is effectively done (brand sheet + logomark + guidelines doc). The DECK is the remaining gap and it is blocked on the palette decision below. | UPD 6 Aug | Row 6
3 | ShaktiAITechLabs | to make pitch deck and brand material for TechLabs | Parth | - | Done | P1 | 6 Aug 2026 | W1-W1 (03 Aug - 09 Aug) | Word doc: logomark, colour system, typography, voice & tone, application standards | Built on the parent Shakti Ecosystem gold/sage/terracotta palette. This CONFLICTS with the existing Nordic Blue brand sheet - see next row. | NEW 6 Aug | Row 7
4 | ShaktiAITechLabs | (decision gate - not a Tasks Sheet row) | Parth | Kushal, Ekata | At risk | P0 | 8 Aug 2026 | W1-W1 (03 Aug - 09 Aug) | One ratified SATL palette + typeface pair, everything else retired | TWO complete brand systems now exist: the brand sheet (Midnight Navy #132238, Neue Montreal/Inter) and today's guidelines doc (gold/sage/terracotta). The 9 Aug deck cannot be built until this is called, and one of the two assets becomes waste either way. | NEW 6 Aug | Row 8
5 | ShaktiAITechLabs | to make pitch deck and brand material for TechLabs (extension) | Parth | - | Not started | P1 | 21 Aug 2026 | W2-W3 (10 Aug - 23 Aug) | Deck template, letterhead, business card, email signature, social templates as editable files | Now blocked on the palette decision. Brand sheet already specifies all 16 assets - this is production, not design. Fix the stale 2024 placeholder dates while producing them. | UPD 6 Aug | Row 9
6 | Shakti.One | to create the entire website and get it connected with all other projects under Shakti Group | Parth | - | In progress | P0 | 16 Aug 2026 | W1-W2 (03 Aug - 16 Aug) | Sitemap, design tokens, component library agreed | Locks the pattern all other group sites reuse - do this before the FC/Greens sites. |  | Row 10
7 | Shakti.One | to create the entire website ... connected with all other projects | Parth | - | Done | P0 | 6 Aug 2026 | W1-W1 (03 Aug - 09 Aug) | SoftSys plan selected, cPanel domain email created, site deployed to public_html and serving | Plans/pricing/security researched and chosen. Site is live on the server but NOT yet reachable on the public domain - that waits on the nameserver switch. | NEW 6 Aug | Row 11
8 | Shakti.One | to create the entire website ... connected with all other projects | Parth | registrar access | At risk | P0 | 7 Aug 2026 | W1-W1 (03 Aug - 09 Aug) | ns33 / ns34.softsyshosting.com set at Namecheap and confirmed | HARD BLOCKER. SSL, HTTPS, live verification, Search Console and every SEO task downstream are all stalled behind this one registrar change. Confirm who holds Namecheap access today. | NEW 6 Aug | Row 12
9 | Shakti.One | to create the entire website ... connected with all other projects | Parth | - | Not started | P0 | 12 Aug 2026 | W1-W2 (03 Aug - 16 Aug) | Site loads on shakti.one, SSL issued, Force HTTPS enabled | 24-48h propagation after the switch. Do not schedule anything domain-dependent inside that window. | NEW 6 Aug | Row 13
10 | Shakti.One | to create the entire website ... connected with all other projects | Parth | - | Not started | P0 | 14 Aug 2026 | W1-W2 (03 Aug - 16 Aug) | Meta description + OG tags, (c) 2026, working form endpoint, venture list reviewed | PULLED FORWARD from W6. Once the site is publicly reachable these stop being pre-launch polish and become live defects that Google indexes: no meta description, no OG tags, footer reads (c) 2025, the contact form has no action, and only 4 of 10 group entities are listed. | NEW 6 Aug | Row 14
11 | Shakti.One | to create the entire website ... connected with all other projects | Parth | - | Not started | P0 | 30 Aug 2026 | W3-W4 (17 Aug - 30 Aug) | Pages for the group entities that should be public + cross-links | Draft lists 4 ventures; the Tasks Sheet tracks 10 entities. Confirm which appear publicly. |  | Row 15
12 | Shakti.One | to create the entire website ... connected with all other projects | Parth | Harsh (CRM) | Not started | P1 | 6 Sep 2026 | W5-W5 (31 Aug - 06 Sep) | Final copy + enquiry form posting into the Sales CRM | Harsh's CRM is already live for Orena - reuse that instance rather than a new endpoint. |  | Row 16
13 | Shakti.One | to create the entire website ... connected with all other projects | Parth | - | Not started | P1 | 16 Aug 2026 | W2-W3 (10 Aug - 23 Aug) | GA4 + Search Console verified, sitemap.xml + robots.txt, canonical URLs | Was 'Deploy + analytics + SEO base' at W6. Deploy half is now done, and the rest moved forward to W2 because a live site with no analytics and no Search Console is a fortnight of lost baseline data. | UPD 6 Aug | Row 17
14 | Fine Circuits | Creation of Pitch deck and details for Fine Circutis | Parth | Ekata, Kushal | Not started | P0 | 30 Aug 2026 | W4-W5 (24 Aug - 06 Sep) | Fine Circuits capability/sales deck | Needed BEFORE the September VVDN / Semicon Haryana travel - that trip is the real deadline. |  | Row 18
15 | Fine Circuits | Designing for WEbsite for Fine Circuits and SEO implementation | Parth | - | Not started | P1 | 20 Sep 2026 | W6-W7 (07 Sep - 20 Sep) | Design comps for the Fine Circuits site | Reuses the Shakti.One design system. Needs product/capability content from Kushal's team. |  | Row 19
16 | Fine Circuits | Designing for WEbsite for Fine Circuits and SEO implementation | Parth | - | Not started | P1 | 4 Oct 2026 | W8-W9 (21 Sep - 04 Oct) | Live Fine Circuits site | Same SoftSys/cPanel route as shakti.one - reuse the runbook. | UPD 6 Aug | Row 20
17 | Fine Circuits | Designing for WEbsite for Fine Circuits and SEO implementation | Parth | Ayush, Ekata (DM) | Not started | P1 | 25 Oct 2026 | W10-W12 (05 Oct - 25 Oct) | Keyword map, on-page SEO, technical SEO, indexing verified | Depends on the 'digital marketing plan / target market' task (Ayush+Ekata) - keywords cannot be chosen before the target market is fixed. |  | Row 21
18 | ShaktiGreens | to create the website | Parth | Ayush, Ekata | Not started | P2 | 11 Oct 2026 | W9-W10 (28 Sep - 11 Oct) | Design comps for ShaktiGreens | Blocked on the 'branding of the location' task (Ayush+Ekata) and the business model. |  | Row 22
19 | ShaktiGreens | to create the website | Parth | - | Not started | P2 | 25 Oct 2026 | W11-W12 (12 Oct - 25 Oct) | Live ShaktiGreens site with enquiry flow | Hospitality/events - enquiry + gallery are the two things that matter. |  | Row 23
20 | Shakti.One | (derived) SEO across group properties | Parth | Ayush, Ekata | Not started | P2 | 8 Nov 2026 | W12-W13 (19 Oct - 01 Nov) | Unified GA4 property, Search Console for all domains, monthly reporting sheet | Do once for all sites instead of per-site. |  | Row 24
21 | Shakti Streets | 3D rending of Shakti Streets to be done | Parth | Surbhi (drawings) | Not started | P1 | 13 Sep 2026 | W5-W6 (31 Aug - 13 Sep) | Plans, materials, reference set, scene scale locked | Cannot start without architectural drawings/plan. Raise with Surbhi in week 5. |  | Row 25
22 | Shakti Streets | 3D rendering OR model to be designed that can be moved inside | Parth | - | Not started | P1 | 4 Oct 2026 | W7-W9 (14 Sep - 04 Oct) | Navigable interior model (walkthrough, not just stills) | 'Can be moved inside' = interactive walkthrough. Decide engine (web/WebGL vs offline render) before modelling. |  | Row 26
23 | Shakti Streets | 3D rending of Shakti Streets to be done | Parth | Kushal (review) | Not started | P1 | 18 Oct 2026 | W10-W11 (05 Oct - 18 Oct) | Final renders + hosted walkthrough link | Higgsfield subscription is 1-month only - schedule it against this window if used. |  | Row 27
24 | Alpha.kore | business model for .dwg and bom making application with Harshit | Hitarth, Parth | Harshit | In progress | P1 | 14 Aug 2026 | W2-W2 (10 Aug - 16 Aug) | Written findings from the demo: what exists, what is missing for a product | Status in sheet = 'GUI in making'. |  | Row 28
25 | Alpha.kore | business model for .dwg and bom making application | Hitarth, Parth | - | Not started | P1 | 23 Aug 2026 | W3-W4 (17 Aug - 30 Aug) | Pricing, ICP, packaging, go-to-market for the DWG/BOM tool | Hitarth leads commercial, Parth leads product/UX framing. |  | Row 29
26 | Alpha.kore | ... after seeing the demonstration and convertiing in product | Parth | Hitarth, Harshit | Not started | P2 | 20 Sep 2026 | W5-W7 (31 Aug - 20 Sep) | Productised GUI, onboarding flow, brochure | Feeds the TechLabs 'product brochures for each product' task. |  | Row 30
27 | Orena Solutions | (NOT IN TASKS SHEET - work already delivered) | Parth | - | Done | P0 | 5 Aug 2026 | W1-W1 (03 Aug - 09 Aug) | ORENA_Product_Vision_Draft.docx - 10 sections, 9 modules, 3-version roadmap | ADD THIS TO THE TASKS SHEET. Roadmap still carries no dates, effort or cost. |  | Row 31
28 | Orena Solutions | (NOT IN TASKS SHEET - work already delivered) | Parth | - | Done | P0 | 5 Aug 2026 | W1-W1 (03 Aug - 09 Aug) | Mentza_ORENA_Integration_Strategy.docx - 9 sections, vendor-abstraction principle | ADD THIS TO THE TASKS SHEET. Needs a revision: it says 'another LMS' where Moodle is in fact already in production, and its colour key (amber = Mentza) contradicts ORENA_PLAN.png (amber = Moodle). |  | Row 32
29 | Orena Solutions | (NOT IN TASKS SHEET - work already delivered) | Parth | - | Done | P0 | 5 Aug 2026 | W1-W1 (03 Aug - 09 Aug) | ORENA_PLAN.png - 5-stage flow, 3 pillars, ownership legend | ADD THIS TO THE TASKS SHEET. Will need re-rendering after the logo palette decision. |  | Row 33
30 | Orena Solutions | (NOT IN TASKS SHEET - work delivered 6 Aug) | Parth | - | Done | P0 | 6 Aug 2026 | W1-W1 (03 Aug - 09 Aug) | Integration mapped across Hiring / Training / Culture + full slide-by-slide content for the CEO pitch | Confirms Moodle is LIVE in production at Orena (candidate screening quizzes). That resolves the doc-vs-diagram contradiction in Moodle's favour - now fold it back into the strategy doc. | NEW 6 Aug | Row 34
31 | Orena Solutions | (NOT IN TASKS SHEET - proposed) | Parth | Ekata | Not started | P0 | 12 Aug 2026 | W1-W2 (03 Aug - 16 Aug) | Built PowerPoint deck for Orena CEO / leadership | Content is fully written, so this is production only. Tomorrow's priority. Deck palette depends on the Orena logo decision - do that first or the deck gets rebuilt. | NEW 6 Aug | Row 35
32 | Orena Solutions | (NOT IN TASKS SHEET - proposed) | Parth | Ekata, Kushal | At risk | P0 | 14 Aug 2026 | W1-W2 (03 Aug - 16 Aug) | Confirmed API surface, auth model, data ownership, rev-share and exit terms | Mentza publishes NO public API docs - Phase 1 cannot be scoped or estimated without this call. External party, so book it now. Use the same call to close the commercial gap the strategy doc leaves open. | NEW 6 Aug | Row 36
33 | Orena Solutions | (NOT IN TASKS SHEET - work delivered 6 Aug) | Parth | - | Done | P1 | 6 Aug 2026 | W1-W1 (03 Aug - 09 Aug) | Word doc: recovered logo recoloured, colour system, typography, voice & tone, application standards | Delivered against the proposed charcoal/amber palette, which is not yet ratified - see next row. | NEW 6 Aug | Row 37
34 | Orena Solutions | (decision gate - not a Tasks Sheet row) | Parth | Orena leadership | At risk | P0 | 7 Aug 2026 | W1-W1 (03 Aug - 09 Aug) | One ratified Orena palette; all existing collateral re-rendered to match | THREE palettes are in circulation: green (stated current brand), navy/teal (the logo actually used in ORENA_PLAN.png), and charcoal/amber (today's proposal). Note amber already means 'Moodle layer' in that diagram's legend, so charcoal/amber collides with it. This is Orena's brand, not ours - leadership calls it. | NEW 6 Aug | Row 38
35 | Orena Solutions | (NOT IN TASKS SHEET - proposed next step) | Parth | Ekata, Het | Not started | P1 | 20 Sep 2026 | W3-W7 (17 Aug - 20 Sep) | Wireframes + UI for V1: Auth, Companies, Hiring, Learning, Experts, Analytics, Documents | The vision doc is explicitly written 'ahead of UI/UX design'. Needs a formal go/no-go before ~25 designer-days are spent - and the Mentza scoping call should land first. |  | Row 39
36 | Orena Solutions | make the complete pitch deck for branding and expansion of Orena | UNASSIGNED | Ekata | Not started | P1 | 27 Sep 2026 | W7-W8 (14 Sep - 27 Sep) | Orena branding + expansion deck | Row has NO owner in the Tasks Sheet. Every other pitch deck is Parth's - confirm ownership or it slips. |  | Row 40
Legend
| P0 | Hard external deadline, or blocking another person's work
| P1 | Committed this quarter
| P2 | Scheduled, but can absorb slip

## Week Calendar
Week Calendar - period numbers used by the Gantt
Type the current week number into 'Period Highlight' (cell H2) on the Project Planner sheet.
Week | Starts (Mon) | Ends (Sun) | Month | Activities starting this week
1 | 03 Aug 2026 | 09 Aug 2026 | August 2026 | SATL - Email IDs for TechLabs + group; SATL - Pitch deck + brand material; SATL - Brand guidelines document; SATL - Palette decision: Nordic Blue vs gold/sage; S1 - Website IA + design system; S1 - SoftSys hosting, cPanel email + deploy; S1 - Namecheap nameserver switch to SoftSys; S1 - DNS propagation, SSL + Force HTTPS; S1 - Live-site fixes: meta, OG, (c) 2026, form; OR - Product Vision document; OR - Mentza integration strategy doc; OR - Platform workflow diagram; OR - Moodle/Mentza integration plan + deck content; OR - Build integration pitch deck (PPT); OR - Mentza scoping call (API + commercials); OR - Brand guidelines document; OR - Logo palette decision: green vs charcoal/amber
2 | 10 Aug 2026 | 16 Aug 2026 | August 2026 | SATL - Brand kit rollout (templates); S1 - Analytics + SEO baseline; AK - DWG/BOM demo review w/ Harshit
3 | 17 Aug 2026 | 23 Aug 2026 | August 2026 | S1 - Venture pages build; AK - Business model document; OR - V1 UI/UX design (9 modules)
4 | 24 Aug 2026 | 30 Aug 2026 | August 2026 | FC - Pitch deck + company details
5 | 31 Aug 2026 | 06 Sep 2026 | August 2026 | S1 - Content + contact form / CRM wiring; SS - 3D asset prep + reference; AK - Product + GUI packaging
6 | 07 Sep 2026 | 13 Sep 2026 | September 2026 | FC - Website design
7 | 14 Sep 2026 | 20 Sep 2026 | September 2026 | SS - 3D walkthrough model build; OR - Branding + expansion pitch deck
8 | 21 Sep 2026 | 27 Sep 2026 | September 2026 | FC - Website build + launch
9 | 28 Sep 2026 | 04 Oct 2026 | September 2026 | SG - Website design
10 | 05 Oct 2026 | 11 Oct 2026 | October 2026 | FC - SEO implementation; SS - Render, review + delivery
11 | 12 Oct 2026 | 18 Oct 2026 | October 2026 | SG - Website build + launch
12 | 19 Oct 2026 | 25 Oct 2026 | October 2026 | GRP - Group SEO + analytics baseline
13 | 26 Oct 2026 | 01 Nov 2026 | October 2026 | -