FINE CIRCUITS AND COMPONENTS PVT LTD  ·  FCCINDIA.COM

SEO Plan

Getting found on Google and AI search

DATE   24 August 2026

COVERS   Next 12 months

ABOUT   Our website, fccindia.com

BASED ON   A full check of our live website on 24 August 2026

STATUS   Draft for review

# 1.  What this is about

SEO means: when someone searches for a circuit board supplier, we come up. Today, mostly, we don't.

Two things have to be true for that to work:

|  | WHAT HAS TO BE TRUE | WHERE WE STAND |
| --- | --- | --- |
| 1 | Our website must say what we can make — in detail, in text a search engine can read. | It doesn't. Our full capability list sits inside a PDF sales deck. |
| 2 | Google must know who we are, clearly and consistently. | It doesn't. We use four different names, and two competitors use one of them. |

### Where we are today

| 24 | 4 | 100 | 0 |
| --- | --- | --- | --- |
| Pages on our website | of those are articles | Words on our main product page | Product data Google can read |

Our sales deck contains 26 technical specifications, 21 testing instruments and a full machine list. None of it is on the website. That is the biggest single opportunity here — and it costs nothing to fix but time.

# 2.  Website health check

|  | WHAT WE LOOKED AT | NOW | WHAT IT MEANS |
| --- | --- | --- | --- |
| ● | Amount of content | RED | 24 pages, 4 articles. Fine-Line Circuits — the competitor sharing our name — has 51. Google has little to show for us. |
| ● | Product page detail | RED | Our multilayer board page has about 100 words of real content. It cannot compete. |
| ● | Technical specifications | RED | All 26 specs are in a PDF. Search engines cannot read them there. |
| ● | Product data tagging | RED | Nothing on our site tells Google “this is a product with these specs”. |
| ● | Company name | RED | Four names in use. Two competitors use one of them. |
| ● | Spelling on live pages | AMBER | Our product page says “DIMENTIONSIONS” and labels a width column “WEIGHT”. |
| ● | Site speed | AMBER | Homepage loads 65 images at once and runs 72 scripts. Slow on phones. |
| ● | Wrong pages listed | AMBER | A test page and an error page are being shown to Google. |
| ● | Google Maps listing | RED | Not claimed for either Vadodara or our US office. It's free. |
| ● | Page titles | GREEN | These are fine. No change needed. |
| ● | Basic setup | GREEN | Website is accessible to search engines. Nothing is blocked. |

# 3.  Search has changed — this matters

Google now answers many questions itself, without sending anyone to a website. So does ChatGPT. Being “number one on Google” is no longer enough.

| 84% | 68% | 34–61% |
| --- | --- | --- |
| of business searches now show an AI answer | of Google searches end with no click | fewer clicks when an AI answer appears |

### What this changes for us

| OLD WAY | NEW WAY |
| --- | --- |
| Get to the top of Google | Be the source Google's AI answer is built from |
| Measure visits to the website | Measure how often we get mentioned, plus real enquiries |
| Write pages for people only | Write pages people and machines can read |
| Hide specs behind a form | Publish specs openly — that is what gets quoted |

THE SIMPLE RULE

AI systems quote specific numbers, not adjectives.

“5,000 sq m per month” gets quoted. “Large capacity” does not.

“UL certificate E235638” gets quoted. “Fully certified” does not.

And every fact should have our name next to it — otherwise we get quoted without the credit.

# 4.  The name problem

We appear online under four different names. Two other circuit board companies use one of them — including a stock-market-listed Indian competitor.

| NAME WE USE | WHERE |
| --- | --- |
| Fineline Circuit Company | Sales deck, LinkedIn link, YouTube |
| Fine Circuits and Components Pvt Ltd | Legal name, website heading |
| FCC India | Website address and page titles |
| FCC Electronics Inc. | US office, separate Facebook page |

| COMPETITOR USING OUR NAME | WEBSITE | WHO THEY ARE |
| --- | --- | --- |
| Fine-Line Circuits Ltd | finelineindia.com | Listed Indian circuit board company. Their site says “India's Leading Printed Circuit Boards Manufacturer”. |
| Fineline Circuits Inc. | finelinepcb.com | A US circuit board company. |

Result: search engines and AI tools cannot tell us apart from them. Our reputation is partly being credited to a competitor.

### The fix

| STEP 1 | Choose FCC India One public name. Keep the legal name for contracts and the website footer only. |
| --- | --- |
| STEP 2 | Change it everywhere in two weeks Website, LinkedIn, YouTube, Google listing, IndiaMART, TradeIndia, directories, email signatures. |
| STEP 3 | Tell Google who we are Add hidden data to our website listing our name, old names, address, founding year and certificates. This is how Google merges us into one company. |
| STEP 4 | Match the UL certificate Our UL safety certificate record must show the same name. It is one of the strongest proofs we own. |

# 5.  What we will build

Build in three stages. Each stage works on its own — we can stop at any of them.

The page count is not a target for its own sake. Google shows one page per search. A single page cannot rank for “teflon PCB manufacturer” and “aerospace PCB supplier” and “metal clad PCB” at the same time — it needs one page for each, or it ranks for none.

### Three stages — pick where to stop

| STAGE | PAGES | WHAT IT GETS US | DO IT? |
| --- | --- | --- | --- |
| 1 · Essential | 20 | Everything we actually sell, plus proof we are credible. Capability pages, quality and certificate pages, and the three pages aimed at buyers leaving China. | Yes — this is the real ask |
| 2 · Recommended | 29 | Adds a page for each industry we serve and local Vadodara/Gujarat pages. Industry pages convert best because buyers search for their own sector. | Yes, by month 6 |
| 3 · Full | ~55 | Adds 28 articles over the year. These build long-term authority and are what AI tools quote. Slower payback, biggest compounding. | Optional — scale to capacity |

IF WE ONLY DO STAGE 1

We still get most of the commercial benefit. Stage 3 is the accelerator, not the engine.

12 articles instead of 28 is perfectly acceptable — it slows compounding, it does not break the plan.

### How we compare today

| COMPANY | PAGES ON THEIR WEBSITE |
| --- | --- |
| FCC India — us | 24 |
| Fine-Line Circuits Ltd — the listed competitor sharing our name | 51 |
| AT&S — global manufacturer | 1,746 |

Measured from their published sitemaps, 24 August 2026. Stage 2 puts us at parity with the competitor currently outranking us for our own name. Stage 3 puts us ahead.

### Where we would end up

| WHAT | TODAY | IN 12 MONTHS |
| --- | --- | --- |
| Pages on the website | 24 | 55 |
| Product / capability pages | 5 | 12 |
| Industry pages | 0 | 7 |
| Articles | 4 | 28 |
| Pages with product data tagging | 0 | 26 |
| Google Maps listings | 0 | 2 |

### The four groups of new pages

| GROUP | PAGES | WHY IT WINS US BUSINESS |
| --- | --- | --- |
| 1. What we can make | Multilayer · Teflon · Metal-clad · Controlled impedance · HDI · Surface finishes · Materials | Engineers search for a capability, not a company. Each page targets one. |
| 2. Who we make it for | Aerospace · Medical · RF · LED lighting · Power · Consumer · Audio | Buyers search for their own industry. These convert best. |
| 3. Why trust us | Quality lab · Certificates · Machines · Customers | This is where the 26 specs and 21 instruments finally go public. |
| 4. Why buy from India | For US buyers · Alternative to China · For Indian companies going local | Chinese boards now cost US buyers 25–30% more in tariffs. These pages catch that demand. |

### Every capability page follows the same shape

| 1 | Clear title What we make, with the key number. Example: “Multilayer PCB Manufacturing — up to 12 Layers”. |
| --- | --- |
| 2 | Short answer 40–60 words directly below, naming us and the key specification. This is the part AI tools quote. |
| 3 | Specification table Real text, not a picture. This is what search engines read. |
| 4 | What affects cost Honest guidance. This is what engineers actually want. |
| 5 | What we need from you Design files, layer stack, target date. |
| 6 | Common questions 5–8 real questions and answers. The format AI quotes most often. |
| 7 | Request a quote A real form — layers, size, quantity, material, file upload. Not “Name, Email, Message”. |

DO NOT HIDE THE SPECIFICATIONS BEHIND A FORM

It is tempting to make people fill in a form to see our capabilities. Don't. Search engines and AI tools cannot fill in forms — so the specs become invisible and the whole plan fails.

Ask for details only at the final PDF download, if at all.

# 6.  Fixes for the website team

Practical jobs, in priority order. Our site runs on WordPress.

| PRI | JOB | WHAT TO DO |
| --- | --- | --- |
| NOW | Fix spelling on live pages | “DIMENTIONSIONS” → “DIMENSIONS”. Column “WEIGHT” → “WIDTH”. Check all five product pages. |
| NOW | Publish the specifications | All 26 specs as a normal web table. Get an engineer to verify each number first — see page 9. |
| NOW | Add product data tagging | Hidden code that tells Google each spec is a fact about a product. |
| NOW | Set up Google + Bing tools | So we can see what people search for. Bing matters — it feeds ChatGPT. |
| NOW | Allow AI crawlers | Confirm ChatGPT, Claude and Perplexity are allowed to read our site. If blocked, we can never be quoted. |
| HIGH | Hide the test pages | A test page and an error page are being shown to Google. Remove both. |
| HIGH | Speed up the homepage | 65 images load at once; only 14 wait until needed. Fix all of them. Reduce the 72 scripts. |
| HIGH | Add LinkedIn tracking tag | Without it we cannot measure or target LinkedIn advertising. |
| HIGH | Link pages to each other | Right now pages barely link internally. Every capability page should link to related industries and back. |
| LATER | Separate India and US pages | Tell Google which pages are for which country. |

# 7.  Getting listed everywhere else

AI tools decide who to recommend by checking whether many sources agree. So our details must match everywhere — exactly.

| WHERE TO LIST | MARKET | WHY |
| --- | --- | --- |
| Google Business Profile | Both | Free. Decides if we appear on Maps. Claim Vadodara and Elk Grove Village. |
| IndiaMART | India | India's largest B2B marketplace. Real buyers search here. |
| TradeIndia | India | Same reason. |
| PCB Directory | Global | Industry-specific. Buyers in our exact category. |
| Europages / Kompass | Europe | European buyer directories. |
| Thomasnet | US | For our US office. |
| ELCINA / IPC | Industry | Industry body listings. Strong credibility signal. |

THE BORING PART THAT MATTERS MOST

Same name. Same address. Same specifications. Same certificates. On every single listing.

This is unglamorous work, and it is the highest-value thing we can do outside our own website.

### Links worth chasing

| SOURCE | WHY IT IS WORTH IT |
| --- | --- |
| Our UL certificate record | An independent safety body confirming we are real. The strongest proof available. |
| Machine makers | Schmoll, Camtek, Orbotech, ATMA and Polar publish customer stories. Costs one phone call. |
| Trade magazines | Electronics For You, ELE Times, I-Connect007. Write useful articles, not press releases. |
| Our customers | Turn the four testimonials we already have into proper case studies. |
| Trade shows | Productronica India, 16–18 Sep 2026. The exhibitor listing itself is a valuable link. |

# 8.  How we measure it

Do not judge this by website visitors. Because Google now answers questions itself, visits can fall while business grows. Judge it by enquiries.

| WHAT | TODAY | IN 12 MONTHS |
| --- | --- | --- |
| Pages on the website | 24 | 55 |
| Articles published | 4 | 28 |
| Times AI tools mention us (out of 25 test questions) | 0 | 12 |
| Times AI tools link to us | 0 | 8 |
| Google Maps listings | 0 | 2 |
| Real enquiries per month from search | Measure first | Grow |

### The AI check — once a month

| SETUP | Write down 25 questions a buyer would ask For example: “Best multilayer PCB manufacturers in India”, “UL certified PCB maker in India for medical devices”, “Alternative to a Chinese PCB supplier”. |
| --- | --- |
| MONTHLY | Ask all 25 to ChatGPT, Perplexity, Gemini and Google Same day each month. Record whether we were mentioned, linked, or missing. |
| TRACK | Watch the number go up Expect first mentions after 1–2 months. Real progress at 3–4 months. Anything faster is luck. |

# 9.  The 12-month plan

| MONTH 1 | Clean up Fix the name everywhere · claim both Google listings · fix spelling and speed · set up measurement · publish all 26 specifications · record where we stand today. |
| --- | --- |
| MONTH 2–3 | Build 7 capability pages · 7 industry pages · quality and certificates pages · product data tagging · real quote form · list on all directories · first 6 articles. |
| MONTH 4–6 | Grow 12 more articles · 4 customer case studies · pages for US and Indian buyers · approach trade magazines · first AI visibility report. |
| MONTH 7–12 | Scale Productronica in September · 10 more articles · local Vadodara and Gujarat pages · chase links · review the full year. |

### Who is needed — the core two

These two cannot be skipped. Everything else is optional.

| ROLE | TIME | WHY IT CANNOT BE SKIPPED |
| --- | --- | --- |
| One clear owner (in-house) | Part-time is enough for Stage 1. Full-time for Stage 3. | Someone whose job this is. The most common reason plans like this fail is that nobody owns it — added to an existing role, it stops within six weeks. |
| A process engineer | 4 hours a week | Checks every technical number before it goes live. Wrong specifications online are worse than none — AI tools will repeat them for years. See page 10. |

### Optional — add these to go faster

None of these are required to start. Each buys speed or scale.

| ADD | WHAT IT BUYS US | ROUGH COST | WHEN |
| --- | --- | --- | --- |
| SEO specialist (outside retainer) | Faster technical work, keyword research, monthly monitoring. Without it we move slower and learn by trial. | ₹50–80k / month | From month 2 |
| Web developer | The fixes on page 6 done properly. Our existing website vendor may already cover this. | ₹20–30k, mostly one-off | Month 1 |
| Video production | Factory videos. Big credibility gain and feeds social media too. Cheapest content we own. | ₹40–60k / month, clustered | From month 3 |
| Designer | Spec sheets, diagrams, downloadable guides. Makes content look professional. | ₹15–25k / month | From month 3 |
| Writer | Gets us to 28 articles instead of 12. Pure acceleration. | ₹30–50k / month | From month 4 |

### What it costs

| VERSION | TEAM | PER MONTH |
| --- | --- | --- |
| Lean start | Core two only. Slower, but it works. | ₹60k – 1 lakh |
| Balanced | Core two + SEO specialist + developer | ₹1.3 – 2 lakh |
| Full speed | Everything above | ₹2 – 3.5 lakh |

Start lean. Add only what we are ready to use. These are planning estimates, not quotes — and the core two already sit on our payroll.

# 10.  Things to be careful about

| RISK | WHAT TO DO |
| --- | --- |
| Our specification numbers may be wrong | The sales deck has conversion errors. It says the smallest hole is “5 mils (0.2 mm)” — but 5 mils is 0.13 mm, not 0.2 mm. Similar errors appear in other rows. An engineer must check all 26 numbers before publishing. Once published, AI tools will repeat them for years. |
| Our certificate wording is wrong | The deck says “ISO 9001-1400” and “ISO 9001-4500”. These should be ISO 14001 and ISO 45001 — separate standards. “LCSO” is probably AS9100. Fix before publishing. |
| Capacity has no time unit | “5,000 sq mts” means nothing. Write 5,000 sq m per month. |
| Customer names need permission | ABB, Siemens, Mitsubishi, L&T and Bharat Electronics may not allow us to name them. Get written permission for each logo and each date. |
| We have no search data yet | We could not access Google Search Console or paid keyword tools. The search terms in this plan are based on how buyers think, not verified search volumes. Check them in month one before spending. |
| Results are not instant | Expect visible movement at month 4–6, AI mentions at month 3–4. Judging this at month two will look like failure and won't be. |
| The name change costs a little at first | A quiet month or two on branded searches. Do it once, early. |

# 11.  Words you will hear

| TERM YOU'LL HEAR | WHAT IT ACTUALLY MEANS |
| --- | --- |
| SEO | Making sure we appear when people search. |
| Ranking | What position we appear in on Google. |
| Impressions | How many times we appeared in search results. |
| Click-through rate | How often people click us after seeing us. |
| Zero-click search | A search where Google answers directly and nobody visits a website. Now 68% of searches. |
| AI Overview | Google's own answer at the top of results, written by AI. |
| AEO / GEO | Getting quoted by AI tools like ChatGPT, instead of just ranking on Google. |
| Structured data | Hidden code that tells search engines “this is a product, this is its specification”. |
| Backlink | Another website linking to ours. Acts like a recommendation. |
| Crawler | The automated program that reads our website for Google or ChatGPT. |
| Indexed | A page that search engines have read and stored. |
| Landing page | A page built for one specific search or audience. |
| Directory listing | Our company profile on sites like IndiaMART or PCB Directory. |
| Search Console | Google's free tool showing what people searched to find us. |
| Qualified enquiry | A real buyer with a real requirement — what we actually count. |